## partners-in-scrime
Partners in Scrime
The best team there ever was, working on Minesweeper together
Milestone 2 - Login/Registration Modules Sprint 1
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
SQL Users Database |  | Max Weber | Done | 2021-01-24 | 1
User Class |  | Max Weber | Done | 2021-01-24 | 2
User Business Service |  | Max Weber, Kayla Currier | Done | 2021-01-24 | 2
User Data Service |  | Max Weber | Done | 2021-01-24 | 3
Daily Sync to GitHub |  | Max Weber, Kayla Currier | Done | 2021-01-24
|  |  |  | 2021-01-24 |  | 0/5
Milestone 2 - Login/Registration Modules Sprint 2
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Registration | Server-Side Validation, HTTP Form Post to Controller, Add User to SQL Database, Success Page, Error Page | Kayla Currier | Done | 2021-01-24 | 2 | v
Subitems | Name | Responsible | Status | Date
HTTP Form Post to Controller
Server-Side Validation
Add User to SQL Database
Success Page
Error Page
Login | Username/Password Validation Form, Authenticate Login Through DB, Success Page, Error Page | Kayla Currier | Done | 2021-01-24 | 2 | v
Subitems | Name | Responsible | Status | Date
Username/Password Validation Form
Authenticate Login Through DB
Success Page
Error Page
UI/UX |  | Max Weber, Kayla Currier | Done | 2021-01-24 | 3
Daily Sync to GitHub |  | Max Weber, Kayla Currier | Done | 2021-01-24 | 0 | v
Update Sprint stuff |  | Max Weber, Kayla Currier | Done | 2021-01-24 | 0.5 | v
Design Report |  | Max Weber, Kayla Currier | Working on it | 2021-01-24 | 0.5 | v
|  |  |  | 2021-01-24 |  | 5/6
Milestone 3 - Initial Game Board Module Sprint 1
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Game Board(available after login) |  | Kayla Currier, Max Weber |  | 2021-02-07 | 2 | v
Display Game Board(Use Razor Syntax and HTML Helpers |  | Kayla Currier |  | 2021-02-07 | 4
Controllers and Business Services | Game Logic, Game Rules | Max Weber |  | 2021-02-07 | 4
Subitems | Name | Responsible | Status | Date
Game Logic
Game Rules
Daily Sync to GitHub
|  |  |  | 2021-02-07 |  | 1/4
Milestone 3 - Initial Game Board Module Sprint 2
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Refactor Login and Registration(As necessary) | Form Validation on Server Side, Save Form Fields in SQL Server relation DB, Success Page, Error Page | Kayla Currier, Max Weber |  | 2021-02-07 | 2 | v
Subitems | Name | Responsible | Status | Date
Form Validation on Server Side
Save Form Fields in SQL Server relation DB
Success Page
Error Page
Main Menu |  | Max Weber, Kayla Currier |  | 2021-02-07 | 2
UI/UX |  | Max Weber, Kayla Currier |  | 2021-02-07 | 3
Daily Sync to GitHub |  | Max Weber, Kayla Currier |  | 2021-02-07 |  | v
Update Sprint Stuff |  | Max Weber, Kayla Currier |  | 2021-02-07 | 0.5 | v
Design Report |  | Max Weber, Kayla Currier |  | 2021-02-07 | 0.5 | v
|  |  |  | 2021-02-07 |  | 4/6
Milestone 4 - Final Game Board Module Sprint 1
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Refactor Game Board pages | Use AJAX Forms (to avoid page refreshes), Use Partial Pages (to avoid page refreshes), Use Partial Views (to promote reuse and modularity) | Max Weber, Kayla Currier |  | 2021-03-07 | 3 | v
Subitems | Name | Responsible | Status | Date
| Use AJAX Forms (to avoid page refreshes) | Max Weber
| Use Partial Pages (to avoid page refreshes) | Kayla Currier
| Use Partial Views (to promote reuse and modularity) | Max Weber, Kayla Currier
Fully functioning Minesweeer Game Board |  | Max Weber, Kayla Currier |  | 2021-03-07 | 2 | v
Encapsulate all Game Logic & Rules in backend business service |  | Max Weber |  | 2021-03-07 | 2
Daily Sync to GitHub |  | Max Weber, Kayla Currier |  | 2021-03-07 | 0 | v
|  |  |  | 2021-03-07 |  | 3/4
Milestone 4 - Final Game Board Module Sprint 2
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Fully Functioning Login & Registration Pages |  | Kayla Currier |  | 2021-03-07 | 2 | v
Refactor code as identified during peer code reviews & instructor recommendations | OR place refactor work as future scrum task in Scrum Back Log | Max Weber, Kayla Currier |  | 2021-03-07 | 2
Subitems | Name | Responsible | Status | Date
OR place refactor work as future scrum task in Scrum Back Log
Update Sprint Stuff |  | Max Weber, Kayla Currier |  | 2021-03-07 | 0.5 | v
Design Report | ER Diagram, Class Diagrams, Flow Charts | Max Weber, Kayla Currier |  | 2021-03-07 | 0.5 | v
Subitems | Name | Responsible | Status | Date
ER Diagram
Class Diagrams
Flow Charts
Retrospective |  | Max Weber, Kayla Currier |  | 2021-03-07 | 0.5 | v
Daily Sync to GitHub |  | Max Weber, Kayla Currier |  | 2021-03-07
|  |  |  | 2021-03-07 |  | 4/6
Milestone 5 - Save/Restore Game Progress & REST API Sprint 1
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Save Game State |  | Max Weber, Kayla Currier |  | 2021-03-28 | 4 | v
Save Game Results | Number of Clicks, Time spent | Max Weber |  | 2021-03-28 | 2 | v
Subitems | Name | Responsible | Status | Date
Number of Clicks
Time spent
Publish Game Results in REST Service |  | Max Weber, Kayla Currier |  | 2021-03-28 | 4 | v
Daily GitHub Sync |  | Max Weber, Kayla Currier |  | 2021-03-28 |  | v
|  |  |  | 2021-03-28 |  | 4/4
Milestone 5 - Save/Restore Game Progress & REST API Sprint 2
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Code Cleanup |  | Max Weber, Kayla Currier |  | 2021-03-28 | 3
Update Sprint stuff |  | Max Weber, Kayla Currier |  | 2021-03-28 | 0.5 | v
Retrospective |  | Max Weber, Kayla Currier |  | 2021-03-28 | 0.5 | v
Design Report |  | Max Weber, Kayla Currier |  | 2021-03-28 | 0.5 | v
Daily GitHub Sync |  | Max Weber, Kayla Currier |  | 2021-03-28
|  |  |  | 2021-03-28 |  | 3/5
Milestone 6 - Final Project/Presentation: Completed Game Sprint 2
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
IoC dependency injection |  | Max Weber, Kayla Currier |  | 2021-04-18 | 3
HTTP Request filter(page security?) |  | Max Weber, Kayla Currier |  | 2021-04-18 | 3
|  |  |  | 2021-04-18 |  | 0/2
Milestone 6 - Final Project/Presentation: Completed Game Sprint 2
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
Code Cleanup |  | Max Weber, Kayla Currier |  | 2021-04-18 | 1
Final Retrospective |  | Max Weber, Kayla Currier |  | 2021-04-18 | 1 | v
Project Presentation |  | Max Weber, Kayla Currier |  | 2021-04-18 | 1 | v
Final Sprint Stuff |  | Max Weber, Kayla Currier |  | 2021-04-18 | 1 | v
Final Design Report |  | Max Weber, Kayla Currier |  | 2021-04-18 | 1 | v
|  |  |  | 2021-04-18 |  | 4/5
Notes
Name | Subitems | Responsible | Status | Due Date | Est. Hours | Deliverables
C O L O R S C H E M E
0/1